## Sheet0
Task | Short Summary | Md Mamun Hossain |  | S M Mahmud Hasan |  | Md Jehadul Hasan |  | Ryota Takeuchi
|  | To Do( With Deadline) | Finishing Date | To Do( With Deadline) | Finishing Date | To Do( With Deadline) | Finishing Date | To Do( With Deadline) | Finishing Date
Task 1 | Designing 3D Parts | Motor Holder, IR sensor Holder, Ultrasonic Sensor Holder Deadline (26.04.2026) | Done (25.04.2026) | Battery Holder Deadline (26.04.2026) | Done (25.04.2026) | Breadboard Holder Deadline (26.04.2026) | Done (26.04.2026) | Sticks & Screw Deadline (26.04.2026) | Done (25.04.2026)
Task 2 | Create SysML Diagrams & Circuit Design | Circuit Design Deadline (20.05.2026) | Done (18.05.2026 | Internal Block Diagram, Sequence Diagram, Activity Diagram,Package Diagram Deadline (20.05.2026) | Done (20.05.2026 | Block Definition Diagram (BDD), Use Case Diagram Deadline (20.05.2026) | Done (18.05.2026 | Requirement Diagram Deadline (20.05.2026) | Done (19.05.2026)
Task 3 | Tinkercad Simulation | Simulation and observing behavior of Motors, IR sensor, ultrasonic sensor Deadline (24.05.2026) | Done (22.05.2026)
Task 4 | Assembly & Wiring | Assembly & Wiring of Arduino, Motors, Motor Driver, Ultrasonic sensor Deadline(29.05.2026) | Done (22.05.2026) | Assembly & Wiring of Arduino, Motors, Motor Driver, Ultrasonic sensor Deadline(29.05.2026) | Done (22.05.2026) | Assembly & Wiring of IR Sensor Deadline(29.05.2026) | Done (22.05.2026) | Assembly & Wiring of IR Sensor Deadline(29.05.2026) | Done (22.05.2026)
Task 5 | Testing Motors & Sensors | Testing IR Sensor Deadline (01.06.2026) | Done (01.06.2026) | Testing Ultrasonic Sensor Deadline (01.06.2026) | Done (01.06.2026) | Testing Motors Deadline (01.06.2026) | Done (01.06.2026) | Testing Motors Deadline (01.06.2026) | Done (01.06.2026)
Task 6 | Coding & Testing | Writing code and Testing Deadline (04.07.2026) | Done (29.06.2026) | Writing code and Testing Deadline (04.07.2026) | Done (29.06.2026) | Testing of the code Deadline (04.07.2026) | Done (29.06.2026) | Testing of the code Deadline (04.07.2026) | Done (29.06.2026)
Task 7 | Final Presentation | Review & Feedback Deadline (05.07.2026) | Done (03.07.2026) | Creating Presentation Deadline (05.07.2026) | Done (03.07.2026) | Helping with content Deadline (05.07.2026) | Done (03.07.2026)
Task 8 | Creating Final Report | Helping with Content Deadline (24.07.2026. | Done (16.07.2026) | Creating Report Deadline (24.07.2026. | Done (16.07.2026) | Helping with Content Deadline (24.07.2026. | Done (16.07.2026) | Helping with Content Deadline (24.07.2026. | Done (16.07.2026)